## Product Backlog
Planned Sprint | Actual Sprint | User Story ID | User Story Description | Estimate (hrs) | MOSCOW | Dependency | Assignee | Status
4 | 4 | SCRUM-118 | API Automation: View All Students Endpoint (Rest Assured) | 10 | MUST HAVE | None | Utkarsh Uttam | To Do
4 | 4 | SCRUM-117 | API Automation: Student Registration Endpoint (Rest Assured) | 9 | MUST HAVE | None | Utkarsh Uttam | To Do
4 | 4 | SCRUM-116 | API Automation: Authentication Endpoint (Rest Assured) | 10 | MUST HAVE | None | Utkarsh Uttam | To Do
3 | 3 | SCRUM-115 | API Testing: View All Students Endpoint (Postman) | 12 | MUST HAVE | None | Utkarsh Uttam | To Do
3 | 3 | SCRUM-114 | API Testing: Student Registration Endpoint (Postman) | 11 | MUST HAVE | None | Utkarsh Uttam | To Do
3 | 3 | SCRUM-113 | API Testing: Authentication Endpoint (Postman) | 13 | MUST HAVE | None | Utkarsh Uttam | To Do