## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 73.5 | 11 | 2 | 5 | 8.5 | 0 | 7.5 | 6 | 2 | 7 | 5 | 3.5 | 2 | 10.5 | 3.5
SPRINT 2 BACKLOG
SCRUM-68 | SCRUM-127 | Test Cases for Username Field | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-68 | SCRUM-128 | Automate Execution for Username | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-68 | SCRUM-129 | Review Test Cases for Username | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-68 | SCRUM-130 | Test case creation for Password | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-68 | SCRUM-131 | Automate execution for password | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 4 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | 0
SCRUM-68 | SCRUM-132 | Review test case results for password | 2025-07-17 | 2025-07-25 | Parth Joshi | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0
SCRUM-68 | SCRUM-133 | Test case creation for sign in button | 2025-07-17 | 2025-07-25 | Parth Joshi | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-68 | SCRUM-134 | Automate execution for sign in button | 2025-07-17 | 2025-07-25 | Parth Joshi | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-68 | SCRUM-135 | Review test case results for sign in button | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-136 | Test case creation - Student name field | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-69 | SCRUM-137 | Automate execution - Student name field | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-69 | SCRUM-138 | Review test case results for Student Name field | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-139 | Test case creation - Mobile number field | 2025-07-17 | 2025-07-25 | Parth Joshi | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-69 | SCRUM-140 | Automate execution - Mobile number field | 2025-07-17 | 2025-07-25 | Parth Joshi | System Test | Done | 4 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | 0
SCRUM-69 | SCRUM-141 | Review test case results for Mobile number field | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0
SCRUM-69 | SCRUM-142 | Test case creation - Email ID field | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-143 | Automate execution - Email ID field | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-69 | SCRUM-144 | Test case creation - CGPA field | 2025-07-17 | 2025-07-25 | Aman Kumar | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-145 | Automate execution - CGPA field | 2025-07-17 | 2025-07-25 | Aman Kumar | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-69 | SCRUM-146 | Review test case results for CGPA field | 2025-07-17 | 2025-07-25 | Parth Joshi | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-69 | SCRUM-147 | Test case creation - Register button | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-148 | Automate execution - Register button | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-69 | SCRUM-149 | Review test case results for Register button | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 4 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | 0
SCRUM-69 | SCRUM-150 | Test case creation - Department Name | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0
SCRUM-69 | SCRUM-151 | Automate Execution - Department Name | 2025-07-17 | 2025-07-25 | Neha G | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-152 | Testcase Review - Department Name | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-69 | SCRUM-153 | Test Case Creation – Backlog Count | 2025-07-17 | 2025-07-25 | Aman Kumar | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-69 | SCRUM-154 | AutomateExecution – Backlog Count | 2025-07-17 | 2025-07-25 | Aman Kumar | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-69 | SCRUM-155 | Testcase Review - Backlog Count | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 3 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0.5
SCRUM-70 | SCRUM-156 | Test data in accordance with roll number | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 2 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0
SCRUM-70 | SCRUM-157 | Automate Test data in accordance with roll number | 2025-07-17 | 2025-07-25 | Utkarsh Uttam | System Test | Done | 1.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SCRUM-70 | SCRUM-158 | Review Test data in accordance with roll number | 2025-07-17 | 2025-07-25 | Sambhram Mathad | System Test | Done | 4 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | 0